## Sheet1
Risk No | Risk Item | Risk Level | Risk Frequency
1 | The Core function not work | Very high | Very Low
2 | Not able Connect Backend | Very high | Very Low
3 | Processing too long time | Medium | Medium
4 | Bad UI desgin | Low | High
5 | Bad UX design | Mediu | High
6 | Not able save the new Image | Low | Low
Risk No | Explaiin | Solution
1 | These are the core for this project | Make sure at least one of these functions able to work
2 | As this is a web based application which mean it must required a backend to success all of these functions
3
4
5
6